## Summary
No | Type | Batch Name | LOT | Location | Onboarding Date | Batch Start Date | L1 Date (Before Lockdown) | Proposed L1 Date | Initial Batch Size | Dropout/Absconded | Transfer In | Transfer Out | Current Batch Size | CG Mentor | TY Mentor | TY Mentor Contact Number | Learning and Assessment Status | Module Assessment (If applicable for current week) | Overall Performance of Candidates on Mock/Module Assessment | L&D Connect/Visit | BU Connect/Visit | Proposed PLP Evaluation Date | PLP Evaluator (Evaluator Name & BU) | Over all Passing Count
1 | Regular HTD | JavaFS 20th Jan | Java | Bangalore | 2020-01-20 | 2020-01-20 | 2020-04-17 | 2020-06-11 | 38 | 7 | 0 | 0 | 31 | Sudheer | Apoorva | 9916669784 | Parallel project evaluation is completed Revision sessions on Core java, Hibernate, Spring MVC is completed | Not conducted |  |  |  | 2020-06-08
2 | Regular HTD | Automation Testing | Automation | Bangalore | 2020-01-20 | 2020-01-20 | 2020-04-17 | 2020-05-25 | 57 | 3 | 0 | 0 | 54 | Neelima | Apoorva | 9916669784 | PLP evaluations + L1 mock is completed Revision on M1 & M2 is conducted to improve their performance in L1 | Not conducted |  |  |  | 2020-05-21
2 | Regular HTD | Java FS | Java | Bangalore | 2020-02-05 | 2020-02-05 | 2020-05-05 | 2020-07-24 | 39 | 1 | 0 | 0 | 38 | Mohammed | Priyanka MS | 9986747552 | Completed SQL Sessions Started JDBC & Servlets sessions online Module 2 - Completed JDBC Mock assessment Mock assessment results has been shared to Mohammed | Conducted Module 2(JDBC) mock assessment | Module 2 (JDBC) results - Good - 9 Average - 19 Needs improvement - 10 Weak Participant's names Lahari Alekya Akileshwar Nikil yedde Pavani Mallikarjun rao Sricharan Swetha Jyothirmai |  |  | 2020-07-21
3 | Regular HTD | Dot Net FullStack | Dot Net FullStack | Bangalore | 2020-02-05 | 2020-02-05 | 2020-05-05 | 2020-06-26 | 42 | 10 | 0 | 0 | 32 | Shital | Abhilash | 8660102182 | Web API online sessions completed TDD & BDD is in progress Parallel Project Phase 3 is completed | Not conducted | Module 1 results - Good - 15 Average - 11 Needs improvement - 5 Weak Participants list Kumari Shalini Aryan Suman Anamramya Nikhil Neelkant Myanamwar Dyvala Gangdhar |  |  | 2020-06-22
4 | Regular HTD | Java Cloud Feb 10th | Java Cloud | Bangalore | 2020-02-10 | 2020-02-10 | 2020-05-11 | 2020-07-02 | 30 | 7 | 7 | 0 | 30 | Mohammed | Chandan | 8073313708 | Angular, Unix sessions & AWS is completed Started Microservices sessions online Sprint 2 Project execution is in progress Module 4 assessment on AWS (practical deployment exercise) has been completed Mock on Angular is completed | Mock on Angular has been done | Mock results (Angular) - Good - 14 Average - 5 Needs Improvement - 2 Weak participants name Pithani Vyshnavi Poonam Raghuwanshi |  |  | 2020-06-29
5 | Regular HTD | Java Abridge | Java Abridge | Bangalore | 2020-02-24 | 2020-02-24 | 2020-04-15 | 2020-06-05 | 21 | 0 | 0 | 0 | 21 | Ganesh | Chandan | 8073313708 | All courses completed PLP is completed L1 is completed |  |  |  |  | 2020-05-28
6 | Regular HTD | Dot Net FullStack 6th March | Dot Net FullStack | Bangalore | 2020-03-06 | 2020-03-06 | 2020-06-04 | 2020-07-23 | 91 | 16 | 0 | 0 | 75 | Manish | Rohit | 9897145195 | ASP.Net MVC sessions online is in progress Started Angular sessions online Parallel Project (phase 1 & 2) execution is in progress Module assessment results (on ASP.NET & ADO.NET ) are shared to Manish | Module 2 Assessment (ASP.NET & ADO.NET) | Module 2 results - Good - 15 Average - 49 Needs Improvement - 11 Weak participants name 1. Jyoti Kumari 2. Kampili Sekhar 3. Chokkapu Chandana 4. Deekshith D S 5. Durga Prasad Ollu 6. Nalluri Pedababu 7. Naveen Kumar Laggani 8. S Chidambar Rao 9. Singampalli Jahnavi Venkata Ramana 10. Vinaykumar Ravuri 11. Ashish A G |  |  | 2020-07-20
7 | Regular HTD | Automation Testing 6th March | Automation | Bangalore | 2020-03-06 | 2020-03-06 | 2020-06-04 | 2020-07-24 | 63 | 5 | 0 | 0 | 58 | Shubhangi | Sudhanshu | 8770134456 | Core Java sessions online (OOPS) is in progress Parallel Project on Manual testing in progress Mock assessment on Modue 2 is conducted | Mock assessment on Module 2 : Manual Testing | Mock on Manual Testing Good - 24 Average - 24 Needs Improvement - 11 Weak participants name 1. Bhagya Sree 2. Kanchana Meghavarapu 3. Kolla Jahanvi 4. M. Aiswarya Sudha 5. Polu Binath Yadav 6. Badai Radhika 7. Manisha 8. Keerthana 9. Sahithi Dande 10. Supriya Chindam 11. Bhavani Devi Ayyaluri |  |  | 2020-07-21

## JEE Abridge Batch Candidates
| Initial Batch Size | 21
| Dropout/Absconded | 0
| Current Batch Size | 21
Attendees List | [6 empty] | Dropout List
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Mukesh Reddy Bomma | Mukesh Reddy | Bomma | Male | 8096741045 | mukesh.bomma@gmail.com
2 | Geetha Lakshmi. Tadi | Geetha Lakshmi | Tadi | Female | 7285915265 | geethalakshmi612@gmail.com
3 | Nalabolu kavya | Nalabolu | Kavya | Female | 9177598388 | nalabolukavya07@gmail.com
4 | Prabakaran S | Prabakaran | S | Male | 8098788737 | prabhaselva22@gmail.com
5 | Suyash Arvind Rameshware | Suyash | Rameshware | Male | 9511794388 | suyash1105@gmail.com
6 | Kota Ramadevi | Rama | Devi | Female | 9000807962 | ramab.tech525@gmail.com
7 | Ritwik Yadav | Ritwik | Yadav | Male | 8109332048 | ryritwikyadav5@gmail.com
8 | Shazia sultan | Shazia | Sultan | Female | 7061427717 | shaziasltn127@gmail.com
9 | Loka Dixith Reddy | Dixith Reddy | Loka | Male | 9505514745 | dikshithloka25@gmail.com
10 | Munagala Vijay | Vijay | Munagala | Male | 9491381997 | vijaychary8@gmail.com
11 | Maddela Vinod Chandra | Vinod Chandra | Maddela | Male | 9493115665 | vinodchandra1730@gmail.com
12 | Amaravathi Amrutha lahari | Amrutha lahari | Amaravathi | Female | 9515482318 | amaravathilahari@gmail.com
13 | Gundulur aneefa | Aneefa | Gundulur | Female | 7993950467 | Aneefa446@gmail.com
14 | Manasi Jayawant Sutar | Manasi | Sutar | Female | 7083788695 | manasisutar14@gmail.com
15 | Rupesh Kumar Kothi | Rupesh Kumar | Kothi | Male | 8978408575 | rupeshkothi000@gmail.com
16 | Savanam Geetha Sri | Savanam | Geetha Sri | Female | 6281296092 | Srigeetha679@gmail.com
17 | Veeranki Gnanika | Veeranki | Gnanika | Female | 8497917088 | gnanikaprasadveeranki@gmail.com
18 | Peter F Lopis | Peter | Lopis | Male | 9483765176 | fpeterlopis1998@gmail.com
19 | Malkapurapu chandu | Malkapurapu | Chandu | Male | 9676046060 | chanduvarma9676@gmail.com
20 | Kasoju Pavan Kumar | Pavan Kumar | Kasoju | Male | 8801221751 | pavankasoju1997@gmail.com
21 | Vamshi Krishna P | Vamshi Krishna | P | Male | 8712880804 | vamshipattem6@gmail.com

## JEE Cloud Batch Candidates (hidden)
| Initial Batch Size | 38
| Dropout/Absconded | 13
| Current Batch Size | 25
Attendees List | [6 empty] | Dropout List
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Chaithra H C | Chaithra | H C | Female | 8105222672 | deepachai1997@gmail.com | 1 | Shalini Priya | Female | 7415469897 | shalinipriya9876@gmail.com
2 | Dhanush V | Dhanush | V | Male | 9036302040 | dhanushvenkatesh176@gmail.com | 2 | Degala Jaswanth Sai | Male | 9902645902 | degalajaswanthsai@gmail.com
3 | Navami D Saliyan | Navami | D Saliyan | Female | 9449379906 | navamisaliyan@gmail.com | 3 | Drakshayanamma B R | Female | 8495964571 | drakshayanammabr@gmail.com
4 | Nethra A S | Nethra | AS | Female | 9449081645 | nethrapriya3731@gmail.com | 4 | Meet Prakashbhai Lad | Male | 8097408972 | meetprakashbhailad@gmail.com
5 | Rajat Agrawal | Rajat | Agrawal | Male | 8109688225 | rajatagrawal355@gmail.com | 5 | Nishi Chaturvedi | Female | 8318388178 | nishichaturvedi@gmail.com
6 | Sree Kumar M U | Sree Kumar | M U | Male | 7892606510 | sreekumar199824@gmail.com | 6 | Pooja Desai | Female | 9019122521 | poojadesai@gmail.com
7 | Khushbu Kumari | Khushbu | Kumari | Female | 9110027171 | khushbukumari3031@gmail.com | 7 | Pooja Kalyani Chinchansur | Female | 9620261963 | poojakalyanichinchansur@gmail.com
8 | Atthuluri Ramya | Atthuluri | Ramya | Female | 7702490441 | atthulurijntu303@gmail.com | 8 | Sai Vamsi Raj Mulagada | Male | 8367670006 | saivamsirajmulagada@gmail.com
9 | Gayathri MM | Gayathri | MM | Female | 9497423461 | gayathrimm1997@gmail.com | 9 | Shalini Priya | Female | 8003451481 | shalinipriya@gmail.com
10 | Humera Khanam.A | Humera | Khanam | Female | 9655267158 | humerasep03@gmail.com | 10 | Soumyasri Ghorai | Female | 7980983990 | soumyasrighorai@gmail.com
11 | Abhinav Kumar | Abhinav | Kumar | Male | 7004203367 | abhinavkmr241@gmail.com | 11 | Srinidhi K M | Male | 8971585572 | srinidhikm@gmail.com
12 | Komathi K | Komathi | K | Female | 9611584123 | komadhu1607@gmail.com | 12 | Vaishnavi G Prasad | Male | 7019173922 | vaishnavigprasad@gmail.com
13 | Mayuri Jain | Mayuri | Jain | Female | 9148687346 | mayurijain08888@gmail.com | 14 | Azra Zaiba Fathima | Female | 8660210756 | azrazaibafathima97@gmail.com
14 | Sri rajeshwari A | Sri rajeshwari | A | Female | 9743827737 | swathigramini1234@gmail.com
15 | Kavitha G N | Kavitha | G N | Female | 9880320581 | kavithagn730@gmail.com
16 | Rohit Kumar | Rohit | Kumar | Male | 8709214319 | rsharma.it40@gmail.com
17 | Abhilasha S | Abhilasha | S | Female | 8217271998 | abhilasha2426@gmail.com
18 | Abhinav Singh | Abhinav | Singh | Male | 7004319764 | abhinavsingh2792@gmail.com
19 | Likitha J | Likitha | J | Female | 8296101268 | likithaj7@gmail.com
20 | Sangeeta Yadav | Sangeeta | Yadav | Female | 8726502156 | ysangeeta175@gmail.com
21 | Pamula Sai Teja | Sai Teja | Pamula | Male | 9494070848 | saitejapst7@gmail.com
22 | Bhagya Lakshmi gnanashekar | Bhagya Lakshmi | Gnanashekar | Female | 7702276400 | bhagyagnanashekaran@gmail.com
23 | Himanshu Shekhar | Himanshu | Shekhar | Male | 8839059445 | luckbest1995@gmail.com
24 | SpoortiChappar | Spoorti | Chappar | Female | 8792935488 | chapparspoorti@gmail.com
25 | Archit Agarwal | Archit | Agarwal | Male | 7055033236 | architagar@gmail.com

## JavaFS Jan20th Batch Candidates
| Initial Batch Size | 38
| Dropout/Absconded | 7
| Current Batch Size | 31
Attendees List | [6 empty] | Dropout List
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Aravind Kesavarapu | Aravind | Kesavarapu | Male | 9493694300 | kesavarapu.aravind@gmail.com | 1 | Bandikatla Vinay Kumar | Male | 9492354363 | b.vinay2630@gmail.com
2 | Bargale Eknath | Bargale | Eknath | Male | 9000757562 | bargaleeknath@gmail.com | 2 | Sriramdas Saichaitanya | Male | 7097668291 | saichaitanya587@gmail.com
3 | Bendi Amulya | Amulya | Bendi | Female | 9963917181 | ammu2315reddy@gmail.com | 3 | Vineeta Gangula | Female | 9492121266 | vineetagangula99@gmail.com
4 | Bhavani Neella | Bhavani | Neella | Female | 9948517510 | varunneella6@gmail.com | 4 | Koniki Sailaja | Female | 8639888652 | konikisailaja@gmail.com
5 | Bijjala Priya | Bijjala | Priya | Female | 9963500545 | bijjalapriya@gmail.com | 5 | Mekala Prasant | Male | 9710799683 | bujjiprasant2677@gmail.com
6 | Channamsetti Ganesh Saradhi | Ganesh Saradhi | Channamsetti | Male | 9884208802 | ganeshsaradhi99@gmail.com | 6 | Sri Lakshmi Thirupathamma Kunduru | Female | 8897323214 | theru.lakshmi74@gmail.com
7 | Gangishetti Vyshnavi | Vyshnavi | Gangishetti | Female | 7659939065 | vyshnavigangishetti@gmail.com | 7 | Sunkari Harshaprakash Reddy | Male | 7095475414 | harshaprakashreddy97@gmail.com
8 | Gurram Naveena Reddy | Naveena Reddy | Gurram | Female | 9393398413 | naveena25.gurram@gmail.com
9 | Injety Vinitha | Vinitha | Injety | Female | 9705560792 | vinithainjety@gmail.com
10 | Joga Nikhitha Rani | Nikhitha Rani | Joga | Female | 9121965361 | joganikhitharani@gmail.com
11 | Jonnala Sai Soumya | Sai Soumya | Jonnala | Female | 9640156716 | jonnala.saisoumya@gmail.com
12 | Kandula Sai Triveni | Kandula | Sai Triveni | Female | 9502981158 | saitriveni160498@gmail.com
13 | Kusuma Sushma | Sushma | Kusuma | Female | 7396600303 | kusumasushma98@gmail.com
14 | Maddi Sahithi | Maddi | Sahithi | Female | 8790456211 | maddisahithi6@gmail.com
15 | Maggidi Vandana | Maggidi | Vandana | Female | 9704381833 | vandana.maggidi@gmail.com
16 | Mallagona Mamatha | Mamatha | Mallagona | Female | 9010554823 | mamathamalagona123@gmail.com
17 | Mutyala Manikanta | Mutyala | Manikanta | Male | 8332891720 | manimutyala888@gmail.com
18 | Peddolla Swapna | Peddolla | Swapna | Female | 7658989533 | swapnar804@gmail.com
19 | Pillalamarri Ankitha | Ankitha | Pillalamarri | Female | 8499918942 | ankithapillalamarri1@gmail.com
20 | Porika Shalini Mishra | Porika Shalini | Mishra | Female | 7330083533 | shaliniporika66@gmail.com
21 | Potlapalli Leela Krishnaveni | Potlapalli | Leela Krishnaveni | Female | 6309475852 | potlapalli.krishnaveni98@gmail.com
22 | Ramyasree Vaitla | Ramyasree | Vaitla | Female | 8328670980 | ramyasreevaitla55@gmail.com
23 | Rudroju Usha Shree | Usha Shree | Rudroju | Female | 7285986982 | usharudroju@gmail.com
24 | Shivarathri Ravi Kumar | Shivarathri | Kumar | Male | 7330300950 | ravikumarshivarathri007@gmail.com
25 | Siddanagari Srinithi | Siddanagari | Srinithi | Female | 8523888272 | srinithisiddanagari@gmail.com
26 | Singireddy Manasa | Manasa | Singireddy | Female | 8374716913 | manasamanureddy802@gmail.com
27 | Soma Pranitha | Soma | Pranitha | Female | 9989291719 | pranithareddy223@gmail.com
28 | Sri Lakshmi Ganjam | Sri Lakshmi | Ganjam | Female | 7093305808 | srilakshmiganjam@gmail.com
31 | Telukula Chinnu | Telukula | Chinnu | Male | 9059937427 | chinnupawan051@gmail.com
32 | Varanasi Vamsi Krishna | Vamsi Krishna | Varanasi | Male | 9948068294 | varanasi.vamsikrishna34@gmail.com
33 | Vishnupriya Cheedella | Cheedella | Vishnupriya | Female | 7396873455 | vishnupriyacheedella@gmail.com

## Automation Batch Candidates (hidden)
| Initial Batch Size | 57
| Dropout/Absconded | 3
| Current Batch Size | 54
Attendees List | [6 empty] | Dropouts
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Akaram Neelima | Neelima | Akaram | Female | 6309075796 | neelimareddyece@gmail.com | 1 | Shaik Shahen Sha Vali | Male | 9640691199 | shahensha269@gmail.com
2 | Akashnika D | Akashnika | D | Female | 8106246336 | akashnikareddy@gmail.com | 2 | Nalla Krishna saiMani Datta | Male | 9912617960 | manidattanalla12@gmail.com
3 | Anem Shanmuka Chandra Teja | Shanmuka Chandra Teja | Anem | Male | 9059942151 | shanmukaanem@gmail.com | 3 | Battu Hemchandh | Male | 9248775588 | hemchandh26@gmail.com
4 | Bachu Saikeerthana | Bachu | Saikeerthana | Female | 7659817939 | saikeerthanabachu@gmail.com
5 | Bammidi Renuka | Renuka | Bammidi | Female | 7036827585 | bammidirenuka06@gmail.com
6 | Bandla Tejasri | Bandla | Tejasri | Female | 7731800812 | tejasribandla984@gmail.com
7 | Bankapuri Avinash | Avinash | Bankapuri | Male | 8688088996 | avinashbankapuri@gmail.com
8 | Begari Saikiran | Saikiran | Begari | Male | 8008555134 | kiransai1011444@gmail.com
9 | Bellamkonda Padmaja | Padmaja | Bellamkonda | Female | 9666191006 | bellamkondapadmaja@gmail.com
10 | Bellamkonda Supriya | Bellamkonda | Supriya | Female | 7730032394 | supriya.bellam5@gmail.com
11 | Chattu Sowmya Sri | Sowmya Sri | Chattu | Female | 9440383708 | chattusowmyasri@gmail.com
12 | Chinnakallepalli Vishnu | Chinnakallepalli | Vishnu | Male | 9704576369 | vishnu192526@gmail.com
13 | Chinthakindhi Ramya Sree | Chinthakindhi | Ramya Sree | Female | 7032728625 | ramyabittu626@gmail.com
14 | Dabbugottu Anusha | Anusha | Dabbugottu | Female | 7901242236 | anushadabbugottu@gmail.com
15 | Daram Sravya | Daram | Sravya | Female | 9573401060 | sravya.daram@gmail.com
16 | Devireddy Siva Gangadhar Rao | Siva Gangadhar Rao | Devireddy | Male | 9908539838 | venkateshdevineddi@gmail.com
17 | Donthurala Prashanth | Prashanth | Donthurala | Male | 9440632622 | prashanthdonthurala56@gmail.com
18 | Dunthula Shravya | Dunthula | Shravya | Female | 7893730552 | shravya213@gmail.com
19 | Gaddam Prashanthi Reddy | Prashanthi Reddy | Gaddam | Female | 8341586250 | prashanthireddy262@gmail.com
20 | Gadde Mounika | Gadde | Mounika | Female | 9603372644 | mounikas4v@gmail.com
21 | Golla Vijaya Lakshmi | Vijaya Lakshmi | Golla | Female | 9494303425 | vijayagolla204@gmail.com
22 | Gudala Preethi | Gudala | Preethi | Female | 8008638242 | preethigudala98@gmail.com
23 | Gujjula Spandana | Spandana | Gujjula | Female | 7893588190 | spandanagujjula21@gmail.com
24 | Indurthi Sahithi | Indurthi | Sahithi | Female | 6303343457 | Sahithi.indurthi97@gmail.com
25 | Ingeetipati Mounika | Ingeetipati | Mounika | Female | 8919795209 | g1mounika961@gmail.com
26 | J.Vaishnavi Reddy | Jaidi | Vaishnavi Reddy | Female | 9951237670 | vaishnavireddyjaidi@gmail.com
27 | Jalwadi Kavya | Kavya | Jalwadi | Female | 8639905365 | jalwadikavya@gmail.com
28 | Jami Thrilekhya | Thrilekhya | Jami | Female | 6302132567 | thrilekhyathrilling73@gmail.com
29 | Kadambari Datta Naga Sai Pavan | Datta Naga Sai Pavan | Kadambari | Male | 9515070334 | pavankadambari33@gmail.com
30 | Kasaram Teja | Kasaram | Teja | Male | 9010400648 | tejakasaram@gmail.com
31 | Kata Hanumanth Puja | Kata | Puja | Female | 8106625428 | katapuja898@gmail.com
32 | Kollati Tanuja | Tanuja | Kollati | Female | 9704171724 | tanujakollati33@gmail.com
33 | Kolli Manasa | Manasa | Kolli | Female | 9100547980 | Kolli.manasa123@gmail.com
34 | Konduru Anusha | Anusha | Konduru | Female | 6304382957 | konduruanusha28@gmail.com
35 | Kowsika V H S Sri Harshavardhan | V H S Sri Harsha Vardhan | Kowsika | Male | 8341314969 | harshakowsika@gmail.com
36 | M Divya | Divya | M | Female | 8142471633 | mdivyadivs@gmail.com
37 | Mallikarjuna Supritha | Supritha | Mallikarjuna | Female | 9701447241 | supritha5454@gmail.com
38 | Mogusala Harika | Harika | Mogusala | Female | 9133280880 | harikamogusala@gmail.com
39 | Mohd Akbar | Mohd | Akbar | Male | 9721736272 | mohdakbar8115@gmail.com
40 | Nalajala.pushpalatha | Nalajala | Pushpalatha | Female | 9441486071 | pushpalathanalajala@gmail.com
41 | Narra SivaPavani | SivaPavani | Narra | Female | 9390205203 | sivapavaninarra@gmail.com
42 | Nithin Surya Reddy Seelapureddy | Nithin Surya Reddy | Seelapureddy | Male | 9100319919 | nithinsuryareddy111@gmail.com
43 | Pamarthi Leelavathi | Leelavathi | Pamarthi | Female | 7995858622 | leelavathipamarthi@gmail.com
44 | Penumallu Viswa Sowrab Reddy | Penumallu Viswa | Sowrab Reddy | Male | 7893434718 | Sowrabreddy1998@gmail.com
45 | Pyla Laxmi Prahelika | Pyla | Prahelika | Female | 8978789485 | lakshmiprahelika@gmail.com
46 | Rajyalakshmi Karnagolla | Rajyalakshmi | Karnagolla | Female | 9502820599 | rajyalakshmi325@gmail.com
47 | Ramidi Upender Reddy | Ramidi Upender | Reddy | Male | 9505305540 | upender.leo@gmail.com
48 | Rapolu Ravi Teja | Rapolu | Ravi Teja | Male | 9492217658 | rapoluravi94@gmail.com
49 | Santhi Augasteena Dasari | Santhi Augasteena | Dasari | Female | 9951854442 | santhi.nov20@gmail.com
50 | Shaik Parveen | Parveen | Shaik | Female | 6301270230 | parveenshaik4p@gmail.com
51 | Sheela.Nikitha | Sheela | Nikitha | Female | 9182681329 | sheela.nikitha@gmail.com
52 | Virigineni Lakshmi Sudha | Virigineni | Sudha | Female | 7036479669 | viriginenilakshmisudha59@gmail.com
53 | Vyamsani Kavya | Vyamsani | Kavya | Female | 9908740809 | kavya.vincy129@gmail.com
54 | Yacham Keerthi | Yacham | Keerthi | Female | 9705817655 | keerthiyecham29@gmail.com

## Java FS Batch Candidates
| Initial Batch Size | 39
| Dropout/Absconded | 1
| Current Batch Size | 38
Attendees List | [6 empty] | Dropouts
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Gurrala Srujana | Gurrala | Srujana | Female | 9515912032 | srujanareddy0331@gmail.com | 1 | Palla Siva Mohan | Male | 7075414457 | sivamohanp07071998@gmail.com
2 | K Chithra | Chitra | K | Female | 7330897090 | kchithra16@gmail.com
3 | Kambala venkata mallikarjun rao | Kambala Venkata | Mallikarjun Rao | Male | 8374431320 | malli.kambala1997@gmail.com
4 | Kancharlapalli Manoj Kumar | Kancharlapalli | Manoj Kumar | Male | 9030110697 | manojkancharalapalli@gmail.com
5 | Kanumilli Sucharitha | Kanumilli | Sucharitha | Female | 9912337576 | kanumillisucharitha408@gmail.com
6 | Kaseemreddy Aparna Reddy | Kaseemreddy | Aparna Reddy | Female | 8341740522 | aparnakusum487@gmail.com
7 | Kolusu Lahari | Kolusu | Lahari | Female | 9177897240 | sailahari33@gmail.com
8 | Konda Rama Lakshmi | Konda | Rama Lakshmi | Female | 7981373816 | ramalakshmikonda654@gmail.com
9 | Kondoju Jayanth | Kondoju | Jayanth | Male | 8008219089 | kondajujayanth@gmail.com
10 | Kota Trikanya | Kota | Trikanya | Female | 8179618742 | k.trikanya1998@gmail.com
11 | Kothapalli S L S Surya Kumari | Kothapalli S L S Surya | Kumari | Female | 7732034152 | suryakothapalli70@gmail.com
12 | Malempati shilpa | Malempati | Shilpa | Female | 6303587986 | 443shilpamalempati@gmail.com
13 | Mandam Jyothirmai | Mandam | Jyothirmai | Female | 7995342795 | mandamjyothirmai95@gmail.com
14 | Manne Veda Vikash | Veda | Vikash | Male | 9490753758 | vikasveda013@gmail.com
15 | Mugala Akhileshwar Reddy | Mugala | Akhileshwar Reddy | Male | 8309408510 | mugalaakhil27@gmail.com
16 | Munnelli Madhuri | Munnelli | Madhuri | Female | 8688533729 | madhurimunnelli98@gmail.com
17 | Muvvala Pujita | Muvvala | Pujita | Female | 9618435065 | poojithamuvvala468@gmail.com
18 | Narahari Maniharika | Narahari | Maniharika | Female | 7702818163 | maniharika.narahari11@gmail.com
19 | Pegadapalli Prathyusha | Pegadapalli | Prathyusha | Female | 8185088739 | pprathyusha457@gmail.com
20 | Pola Ruchitha | Ruchitha | Pola | Female | 7702308564 | Polaruchitha796@gmail.com
21 | Pollapalli Shravika Reddy | Shravika Reddy | Pollapalli | Female | 9502604245 | shravika4245@gmail.com
22 | Ravi Kavitha | Kavitha | Ravi | Female | 9542608958 | ravi.kavitha4321@gmail.com
23 | Sadala Shirisha | Sadala | Shirisha | Female | 9866505106 | s.shirisha.98@gmail.com
24 | Sagar Purumala | Sagar | Purumala | Male | 9642726909 | sagarpurumala@gmail.com
25 | Salapu Upendra | Salapu | Upendra | Male | 8106553645 | salapuupendra18@gmail.com
26 | Sanka.Pranitha | Pranitha | Sanka | Female | 9515066248 | pranitha.173@gmail.com
27 | Shaik. Nagur Baji | Shaik | Nagur Baji | Male | 9908249773 | bajishaik2405@gmail.com
28 | Simhadri Yasasvi Sricharan Koteswara Rao | Simhadri | Yasasvi Sricharan Koteswara Rao | Male | 9441673859 | yasasvisricharan1@outlook.com
29 | Sriram Pavani | Sriram | Pavani | Female | 7207941598 | pavanisriram17@gmail.com
30 | Swetasmin khuntia | Swetasmin | Khuntia | Female | 7978542308 | sweta.smin12334@gmail.com
31 | Tadpalli Nikhil kumar | Nikhil | Kumar | Male | 9515281648 | nipa6025@gmail.com
32 | Thumma Geethika | Thumma | Geethika | Female | 9550364573 | thummageethika@gmail.com
33 | Vanga.Laxmi Prasanna | Vanga | Laxmi prasanna | Female | 9908198054 | prasannareddy2398@gmail.com
34 | Varun Teja Perla | Varun | Teja | Male | 8500844087 | varunteja0549@gmail.com
35 | Veeranki Anusha | Veeranki | Anusha | Female | 8688441105 | anuveeranki3@gmail.com
36 | Vuyyala Swathi | Vuyyala | Swathi | Female | 9515525235 | swadeepu143@gmail.com
37 | Yarrabandla Alekhya | Yarrabandla | Alekhya | Female | 8125707779 | alekhyar083@gmail.com
38 | Yedde Nikhil Kumar | Yedde | Nikhil Kumar | Male | 8179838042 | nikhilkumaryede@gmail.com

## Dot Net FS Batch Candidates
| Initial Batch Size | 42
| Dropout/Absconded | 10
| Current Batch Size | 32
Attendees List | [6 empty] | Dropouts
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Alapati Yeshwanth Reddy | Yeshwanth | Reddy | Male | 8096832346 | yeshwanthalapati@gmail.com | 1 | Atul Kumar Bhadoriya | Male | 7067854900 | atul.kumar@gmail.com
2 | Ankammagari Divya | Ankammagari | Divya | Female | 7396283859 | divyareddy4589@gmail.com | 2 | Palakuru Ojaswini | Female | 8978004208 | palakuru.ojaswini@gmail.com
3 | Annam Ramya | Annam | Ramya | Female | 9490253266 | ramyaannam11@gmail.com | 3 | B.Sri Ajay | Male | 8727838555 | bsriajay@gmail.com
4 | Arudala Triveni | Triveni | Arudala | Female | 7075788483 | triveniarudala0106@gmail.com | 4 | Gentyala Kiranmai | Female | 9733596005 | gentyala.kiranmai@gmail.com
5 | Aryan Sumant | Aryan | Sumant | Male | 8962242597 | aryansumant.as@gmail.com | 5 | Saif Asghar | Female | 9963195527 | saifasghar@gmail.com
6 | Bathini Sai Vinay Kumar | Bathini | Sai Vinay Kumar | Male | 7093901515 | vinaybathini444@gmail.com | 6 | Dhanyamraju Siva Sandeep | Female | 8895246891 | dhanyamrajusivasandeep@gmail.com
7 | Biswarup Dutta | Biswarup | Dutta | Male | 8350023520 | biswarupmainakdutta@gmail.com | 7 | Deepa P R | Female | 7899864470 | deepapr.2810@gmail.com
8 | Butreddy Manasa Reddy | Butreddy | Manasa Reddy | Female | 9573876474 | manasabutreddy19@gmail.com | 8 | Ayasha Khatoon | Female | 7067854900 | ayashak43@gmail.com
9 | Chennuri Priyanka | Chennuri | Priyanka | Female | 9908890985 | nithya.reddy1011@gmail.com | 9 | Bhashyam KeerthiReddy | Female | 7981621801 | bhashyamkeerthireddy@gmail.com
10 | Chepuri Rakesh | Rakesh | Rakesh | Male | 8247414605 | rchepuri999@gmail.com | 10 | Naveen Dogga | Male | 8143505692 | naveendogga01@gmail.com
11 | Chipra Swamy | Chipra | Swamy | Male | 9110742024 | swamychipra@gmail.com
12 | Darshangowda V Y | Darshangowda | V Y | Male | 9448509564 | darshangowda4578100@gmail.com
13 | Doddi Vishnu Vardhan | Vishnu | Vishnu Vardhan | Male | 7989823989 | vishnudoddi0@gmail.com
14 | Dyvala Gangadhar | Dyvala | Gangadhar | Male | 7013524698 | gangadhar.daivala@gmail.com
15 | Gaddam Varshitha | Gaddam | Varshitha | Female | 7729885062 | varshitha1205@gmail.com
16 | Gollapudi Venkata Rajendra Prasad | Gollapudi | Venkata Rajendra Prasad | Male | 7095658780 | nikhil.gollapudi211@gmail.com
17 | Indranil Mukherjee | Indranil | Mukherjee | Male | 9576962432 | indranilmukherjee080@gmail.com
18 | Karthik Konanki | Karthik | Konanki | Male | 8904805198 | karthikkonanki33@gmail.com
19 | Kumari Shalini | Kumari | Shalini | Female | 8727838555 | shalinirajput0501@gmail.com
20 | Manisha Mund | Manisha | Mund | Female | 8895246891 | mundmanisha473@gmail.com
21 | Modunuri Yeswanth Kumar | Yeswanth | Kumar | Male | 9963195527 | yashwanthsanju03@gmail.com
22 | Mohana Kundu | Mohana | Kundu | Female | 9733596005 | mohanakundu0120@gmail.com
23 | Nallapareddi Sushmitha | Nallapareddi | Sushmitha | Female | 8978004208 | nallapareddysushmitha@gmail.com
24 | Nikhil Nilkanth Myanamwar | Nikhil | Nilkanth Myanamwar | Male | 9420774181 | nikhilmyanamwar18@gmail.com
25 | Rishav Kumar | Rishav | Kumar | Male | 9955787506 | rishavdev419@gmail.com
26 | S Sowmya | S | Sowmya | Female | 9966091058 | vinaysowmya123@gmail.com
27 | Sanoj C R | Sanoj | C R | Male | 8281833265 | sanoj.cr@gmail.com
28 | Saripella Saila | Saripella | Saila | Female | 9493844342 | saripellasaila96@gmail.com
29 | Shivam Sharma | Shivam | Sharma | Male | 9431926318 | shivam.27sks@gmail.com
30 | Sogala Rajasekhar Yadav | Sogala | Rajasekhar Yadav | Male | 8500123465 | S.rajsekhar5@gmail.com
31 | Swathi | Kulal | Swathi Kulal | Female | 9900513096 | swathikulal09@gmail.com
32 | Valurouthu Mohini Prasanna | Valurouthu | Mohini Prasanna | Female | 9515997707 | mohiniprasanna1997@gmail.com

## Java Cloud Feb10th Candidates
| Initial Batch Size | 30
| Dropout/Absconded | 7
| Current Batch Size | 30
Attendees List | [6 empty] | Dropouts
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Abinash swain | Abinash | Swain | Male | 8895684335 | swainabinash97@gmail.com | 1 | Vivek Kumar Dixit | Male | 9603074107 | vivek.kumar@gmail.com
2 | Abishek A | Abishek | A | Male | 9600116639 | abishekcse09@gmail.com | 2 | Rajat Kumar Asa | Male | 8185035655 | rajat.kumar@gmail.com
3 | Akshay R Poduval | Akshay | Poduval | Male | 9496673770 | kshpoduval@gmail.com | 3 | G Swetha | Female | 8688578488 | swethachowdary367@gmail.com
4 | Alampalli SaiLikitha | Alampalli | SaiLikitha | Female | 8328240593 | likitha.alampalli@gmail.com | 4 | Roman Rashid | Male | 6200696342 | romirumi123@gmail.com
5 | Amrutha K C | Amrutha | K C | Female | 9480342924 | amruthakc1212@gmail.com | 5 | Saleem M | Male | 8722850530 | Sajb8722@gmail.com
6 | Anant Soni | Anant | Soni | Male | 9713852510 | Sanant640@gmail.com | 6 | Lokesh | Male | 9740694145 | lokeshbhavikatte111@gmail.com
7 | Divyashree K N | Divyashree | K N | Female | 7019585962 | divyashree.kn311@gmail.com | 7 | Chintala Sandhya Kumari | Female | 6304302558 | sandhya.ammulu.0224@gmail.com
8 | Harshitha TB | Harshitha | TB | Female | 7090588713 | tbharshitha8@gmail.com
9 | Jaswanth Kumar Karamala | Jaswanth | Karamala | Male | 9398318945 | jaswanth.karamala@gmail.com
10 | Mayank Singh | Mayank | Singh | Male | 7681093264 | mayanksi191op@gmail.com
11 | Nama Kalyani | Nama | Kalyani | Female | 8790730294 | kalyaninama1997@gmail.com
12 | Nandhakumar Nachimuthu | Nandh kumar | Nachimuthu | Male | 8754733858 | nandharam994453@gmail.com
13 | Poonam Raghuwanshi | Poonam | Raghuwanshi | Female | 8349378230 | poonamraghuwanshi51@gmail.com
14 | Sachin H N | Sachin | H N | Male | 9036995828 | ninasa.sachin@gmail.com
15 | Saswata Biswas | Saswata | Biswas | Male | 7259954836 | mailsaswata15 @gmail.com
16 | Senku Manohar | Senku | Manohar | Male | 8185035655 | senkumanohar11@gmail.com
17 | Somaraju sravani | Somaraju | Sravani | Female | 9603074107 | sravani.somaraju25@gmail.com
18 | Somnath Naik Koli | Somnath | Naik Koli | Male | 9880621750 | somunaik1750@gmail.com
19 | Soumi Bhattacharyya | Soumi | Bhattacharyya | Female | 8617040412 | bhattasoumi@gmail.com
20 | Srinivasavaraprasad C | Srinivasavaraprasad | C | Male | 8105772582 | varaprasadc1997@gmail.com
21 | Swathi R | Swathi | R | Female | 7406268854 | swathir.63112@gmail.com
22 | Tarushi Verma | Tarushi | Verma | Female | 9785774313 | tarushiverma6159@gmail.com
23 | Vyshnavi Pithani | Vyshnavi | Pithani | Female | 9182574443 | vaishnavi7117@gmail.com
24 | Abhinav Singh | Abhinav | Singh | Male | 7004319764 | abhinavsingh2792@gmail.com
25 | Dhanush V | Dhanush | V | Male | 9036302040 | dhanushvenkatesh176@gmail.com
26 | Likitha J | Likitha | J | Female | 8296101268 | likithaj7@gmail.com
27 | Archit Agarwal | Archit | Agarwal | Male | 7055033236 | architagar@gmail.com
28 | Khushbu Kumari | Khushbu | Kumari | Female | 9110027171 | khushbukumari3031@gmail.com
29 | Sri rajeshwari A | Sri rajeshwari | A | Female | 9743827737 | swathigramini1234@gmail.com
30 | Pamula Sai Teja | Sai Teja | Pamula | Male | 9494070848 | saitejapst7@gmail.com

## DotNetFS Mar Batch Candidates
| Initial Batch Size | 91
| Dropout/Absconded | 16
| Current Batch Size | 75
Attendees List | [6 empty] | Dropouts
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | A.Jyoshna | Jyoshna | Anthagoudolla | Female | 8555092559 | 15r91a0405tkrec@gmail.com | 1 | V Shravya | Female | 8500792415 | shravsvemuganti@gmail.com
2 | Abhishek Kolipaka | ABHISHEK | KOLIPAKA | Male | 9912082738 | kolipakaabhi@gmail.com | 2 | Vinayak Venkatraman Hebbar | Male | 7411567712 | vinhebbar11@gmail.com
3 | Abhishek Kumar | Abhishek | Kumar | Male | 7908906819 | ak9852445@gmail.com | 3 | Dudekula Hussain Peerea | Male | 9885678310 | hussainpeera96@gmail.com
4 | Adapa Vinayaka Durga Prasad | Vinayaka Durga Prasad | Adapa | Male | 8639237506 | adapavinay1997@gmail.com | 4 | Raushan Kumar Jha | Male | 9430221958 | raushankumarjha789@gmail.com
5 | Anitha Chinthamreddy | Anitha | Chinthamreddy | Female | 9490626175 | maneeshareddy125@gmail.com | 5 | Rudra Ravali | Female | 9885352157 | ravalirudra291197@gmail.com
6 | Anusha Robert | Anusha | Robert | Female | 8553640622 | anusha.p.robert@gmail.com | 6 | P Vamshi Krishna | Male | 8712880804 | vamshipattem6@gmail.com
7 | Apoorva K G | Apoorva | K G | Female | 9945531261 | apoorvakg1998@gmail.cm | 7 | Kandula Mohan Sai Krishna | Male | 9966345454 | krishnakandula11@gmail.com
8 | Ashish A G | Ashish | A G | Male | 9036602448 | a.g.ashish.jinna@gmail.com | 8 | Peketi Venkata Pradeep Reddy | Male | 9951619663 | peketipradeepreddy@gmail.com
9 | Begari Mahesh | Begari | Mahesh | Male | 9705317221 | maheshbegari95@gmail.com | 9 | Pratikshya Pandav | Female | 7978364830 | pratikshyapandav34@gmail.com
10 | Bhimavarapu Jaya Ramya | Jaya Ramya | Bhimavarapu | Female | 9676111015 | bramyacool@gmail.com | 10 | Sahil Dilip Deosekar | Male | 8830089082 | sahildeosekar1997@gmail.com
11 | Chepyala Ramya | RAMYA | CHEPYALA | Female | 9014715656 | chepyalaramya890@gmail.com | 11 | Suneetha Pisipati | Female | 9346058792 | suneethapisipati934@gmail.com
12 | Chilukuri Priyanka | Priyanka | Chilukuri | Female | 9160565332 | priyankachilukuri612@gmail.com | 12 | Alamkonda Bhaskar Reddy | Male | 7799597224 | bhaskarreddy.alamkonda@gmail.com
13 | Chokkapu Chandana | Chandana | Chokkapu | Female | 9110550834 | chandana.chokkapu1914@gmail.com | 13 | D.Sarika | Female | 8142401876 | sarikahoney97@gmail.com
14 | Deekshith D S | Deekshith | D S | Male | 8971107780 | deekshithcg255@gmail.com | 14 | Bhavya Mallick | Female | 8887725234 | bhavyamallick11@gmail.com
15 | Donthiboina Deepsagarreddy | Donthiboina deepsagar | Reddy | Male | 9676754570 | donthiboinadeepsagarreddy@gmail.com | 15 | Murugan Vengkadaeswara Loganathan | Male | 9688768253 | muruganvengkadaeswara@gmail.com
16 | Durga Prasad Ollu | Durga | Prasad | Male | 8497990548 | ajaykumaryadalapurapu12345@gmail.com | 16 | Mohammad Nayyar Alam | Male | 7488178964 | nayyar017@gmail.com
17 | Edulapalli Sowmya | Sowmya | Edulapalli | Female | 8317613445 | sowmyaedulapalli1997@gmail.com
18 | G.Yeshwanth Kumar | Yeshwanth | Kumar | Male | 9849748156 | yeshwanth7474@gmail.com
19 | Ganesh H | Ganesh | H | Male | 9538104856 | ganeshhs2244@gmail.com
20 | Gopu Likhitha Reddy | Gopu | Likhitha Reddy | Female | 7680068059 | gopulikhithareddy@gmail.com
21 | Injam Harshith | Harshith | Injam | Male | 9440294966 | 150060110@kluniversity.in
22 | Jyoti Kumari | Jyoti | Kumari | Female | 8210945730 | jyotisnd2211@gmail.com
23 | Kampili Sekhar | Sekhar | Kampili | Male | 9948619352 | kampilisekhar1@gmail.com
24 | Kandulaarundhathi | Arundhathi | Kandula | Female | 9652268780 | kandulachiru3@gmail.com
25 | Karakala Kavya | Kavya | Karakala | Female | 9391310169 | kavya3445@gmail.com
26 | Katika Sudarshan Rao | sudarshan | rao | Male | 7989200364 | katikasudarshanrao@gmail.com
27 | Konduru Shanthi Kiran | Shanthi Kiran | Konduru | Male | 9440325279 | kondurusasikala.12@gmail.com
28 | Kothapalli Pranay | Kothapalli | Pranaya | Female | 9177397968 | pranaya141197@gmail.com
29 | Madishetti Hemanth Kumar | Hemanth kumar | Madishetti | Male | 9700106791 | madishettyhemanth999@gmail.com
30 | Mallidi Mounika | Mallidi | Mounika | Female | 9959125222 | mounikareddymallidi535@gmail.com
31 | Mallik Kamisetti | MALLIK | KAMISETTI | Male | 8639079966 | mallikkamisetti05@gmail.com
32 | Manoj Kumar Bollabathini | Manoj Kumar | Bollabathini | Male | 8465090232 | manojkumar.bmk@gmail.com
33 | Matti Pallavi | Pallavi | Matti | Female | 8309656948 | sudhapallavi369@gmail.com
34 | Mittapalli Harika | Harika | Mittapalli | Female | 8297894853 | mittapalliharika98@gmail.com
36 | Mohammed Riyaz | RIYAZ | MOHAMMED | Male | 9494225918 | rizzu1237@gmail.com
37 | Muddam Prasanna | Prasanna | Muddam | Female | 7729870833 | muddamprasanna207@gmail.com
38 | Murari Usha Kiran | MURARI | USHA KIRAN | Female | 8095957949 | kiranmurari2014@gmail.com
39 | N Lakshmi Soujanya | Lakshmi Soujanya | Narra | Female | 7036707144 | lakshmisowjanya799@gmail.com
40 | Nallaralla Himender Reddy | NALLARALLA | HIMENDER REDDY | Male | 7207318161 | himender.nallaralla@gmail.com
41 | Nalluri Pedababu | NALLURI | PEDABABU | Male | 9490125049 | pb16011997@gmail.com
42 | Nama Mamatha | Mamatha | Chowdary | Female | 8978001257 | swathi.gadde06@gmail.com
43 | Naveen Kumar Laggani | NAVEEN KUMAR | LAGGANI | Male | 9959904417 | sidnaveen99@gmail.com
44 | Niriksha P | NIRIKSHA | P | Female | 9513198019 | niriksha972@gmail.com
45 | Niveditha B R | Niveditha | B R | Female | 9632215620 | niveditha924@gmail.com
46 | Nunna Subhramanya Sudheer Kumar | Sudheer | Kumar | Male | 9581116694 | sudheerkumarnunna98@gmail.com
47 | P Durga Neha | Durga Neha | Peram | Female | 7680023222 | peramnehareddy@gmail.com
48 | Paaka Vijayanand Sagar | Vijayanand Sagar | Paaka | Male | 7658916330 | paakasagar@gmail.com
49 | Pallapu Gopichand | Gopichand | Pallapu | Male | 9010327216 | chandhulucky132@gmail.com
50 | Pavan Kumar Reddy Seelam | Pavan Kumar Reddy | Seelam | Male | 8184937464 | seelam328@gmail.com
51 | Pavani Potti | Pavani | Potti | Female | 6300332618 | pavani14898@gmail.com
52 | Podduturi Vinusha | VINUSHA | PODDUTURI | Female | 9866886673 | vinushareddy624@gmail.com
53 | Pranay Verma | Pranay | Verma | Male | 9630723863 | punitverma1996@gmail.com
54 | Preeti Akkatangerhal | Preeti | Akkatangerhal | Female | 9739693373 | preetiashok130@gmail.com
55 | Priyanka Sahoo | PRIYANKA | SAHOO | Female | 8917581057 | priyankasahoo2602@gmail.com
56 | Pushpa Chimma | Chimma | Pushpa | Female | 9704560387 | pushpach2402@gmail.com
57 | Rama Sai Eswara Naidu | Rama Sai Eswara Naidu | Jaddu | Male | 8374134336 | ramsaieswarnaidu.jaddu@gmail.com
58 | S Chidambar Rao | S Chidambar | Rao | Male | 6303323759 | chidambarraos@gmail.com
59 | Sajja Dinesh | Dinesh | Sajja | Male | 6305770875 | sajjadinesh1634@gmail.com
60 | Seemakurthi. Satya Sravani | Satya Sravani | Seemakurthi | Female | 9030992554 | svvssravani@gmail.com
61 | Shaik Rasool | Shaik | Rasool | Male | 9652252373 | shaik.reshma.rs7@gmail.com
62 | Sheshatwam.Dharan Kumar | Dharan kumar | Sheshatwam | Male | 7093379100 | nukalrj@gmail.com
63 | Shubham Kumar Yadav | Shubham | Kumar Yadav | Male | 8416835338 | shubhamyadavr080@gmail.com
64 | Singampalli Jahnavi Venkata Ramana | Jahnavi | Venkata Ramana | Female | 9010028025 | jahnavisingampalli398@gmail.com
65 | Srikanth Reddy Kasam | Srikanth Reddy | Kasam | Male | 7013762759 | srikanthreddyk03@gmail.com
66 | Sudhanshu Bhatt | Sudhanshu | Bhatt | Male | 8464060027 | sudhanshubhatt.1204@gmail.com
67 | Sushanth Sp | Sushanth | Sp | Male | 9066132724 | sushanthsp417@gmail.com
68 | Tunguturi Saiteja | SAITEJA | TUNGUTURI | Male | 9441383361 | sainani0333@gmail.com
69 | Vinayaka M Gowda | VINAYAKA | GOWDA | Male | 9620099005 | v-m-gowda@hotmail.com
70 | Vinaykumar Ravuri | vinaykumar | Ravuri | Male | 7337236725 | Venkatasairampeddi.pvsr@gmail.com
71 | Vintha Vivekananda Reddy | Vivekananda Reddy | Vintha | Male | 9985668719 | vinthavivekanandareddy@gmail.com
72 | Wannal Rajasree | RAJASREE | WANNAL | Female | 8919134762 | rajashree.wannal@gmail.com
73 | Yelchuru Venkata Naga Tejaswi | Tejaswi | Yelchuru Venkata Naga | Female | 6303083177 | tejaswiyelchuru11@gmail.com
74 | Yerra Dinesh Kumar | Dinesh Kumar | Yerra | Male | 8886196611 | yerra.dinesh.346@gmail.com
75 | Yeturu Sai Priya | Sai priya | Yeturu | Female | 8790532966 | saipriya43598@gmail.com
76 | Yogesh Manikanta Gudide | Yogesh Manikanta | Gudide | Male | 8500262642 | manikantagudide@gmail.com

## Automation Mar Batch Candidates
| Initial Batch Size | 63
| Dropout/Absconded | 5
| Current Batch Size | 58
Attendees List | [6 empty] | Dropouts
No. | Name | First Name | Last Name | Gender | Contact No. | Email ID | No. | Name | Gender | Contact No. | Email ID
1 | Annapurna Adapa | Annapurna | Adapa | Female | 9666366789 | purnaadapa@gmail.com | 1 | Teja Sri Lakshmi.Borsu | Female | 7013832218 | srilekhasrilu005@gmail.com
2 | Adabala Rupa Venkata Naga Sai Diwakar | RUPA VENKATA NAGA | SAI DIWAKAR | Male | 9182322622 | saidiwakar2097@gmail.com | 2 | Mayuri Hedau | Female | 7075134401 | mayurihedau09@gmail.com
3 | Afrin Nusrat | Afrin | Nusrat | Female | 7541075703 | afrinnusrat16@gmail.com | 3 | Oduri Suneetha | Female | 8978912128 | suneethaoduri8@gmail.com
4 | Ambula Likhitha Soumya | Likhitha Soumya | Ambula | Female | 8555059691 | ambula97@gmail.com | 4 | Rajamahanti Kumara Guna Chandra | Male | 9849110708 | gunarajamahanti@gmail.com
5 | Ayyaluri Bhavani Devi | Bhavani Devi | Ayyaluri | Female | 9866045513 | bhavaniayyalluri@gmail.com | 5 | Mandalapu Mahesh Babu | Male | 9398834342 | mandalapumahesh1430@gmail.com
6 | Badai Radhika | Radhika | Badai | Female | 7416304491 | radhikabadai96@gmail.com
7 | Beeram Shirisha | Shirisha | Beeram | Female | 9177003052 | shirisha2307@gmail.com
8 | Bhootam Sahithi | Sahithi | Bhootam | Female | 8919941337 | bhootamsahithi@gmail.com
9 | Bimasani Chalapat Rao | Chalapati rao | Bimasani | Male | 9100504165 | sarveshbhimasani@gmail.com
10 | Bongoni Archana | Archana | Bongoni | Female | 9666600597 | archana33bongoni@gmail.com
11 | Chengalwa Naveen | Naveen | Chengalwa | Male | 9160553259 | chengalwa.naveen@gmail.com
12 | Chindam Supriya | Supriya | Chindam | Female | 7337568628 | chindamsupriya9@gmail.com
13 | Dakuri Jagadesh | Dakuri | Jagadesh | Male | 9848322482 | jagadeshwer786@gmail.com
14 | Deshamaina Chandrakanth | Chandrakanth | Deshamaina | Male | 9154806047 | chandrakanth847@gmail.com
15 | Erla Rajkumar | Erla | Rajkumar | Male | 9949190664 | rajkumarsiri18@gmail.com
16 | Eslavath Nandulal Nayak | Nandulal Nayak | Eslavath | Male | 9553558382 | nayaknandulal@gmail.com
17 | G Niharika | Niharika | Gadige | Female | 8328613308 | niharikasarayu96@gmail.com
18 | G.Sriranga Nikhil | Sriranga Nikhil | Gudipati | Male | 9618344975 | srirangasri7@gmail.com
19 | Gali Keerthana | Keerthana | Gali | Female | 8340804549 | galikeerthi163@gmail.com
20 | Hirak Jyoti Chakraborty | Hirak | Chakraborty | Male | 7478107725 | hirakchakraborty99@gmail.com
21 | Kaluvakolu Subhash | Subhash | Kaluvakolu | Male | 6300522519 | kalvakolusubhash@gmail.com
22 | Kasaramoni Keerthi Sai | Keerthi Sai | Kasaramoni | Male | 9381672460 | ksaiy9@gmail.com
23 | Kasturi Kavya | Kavya | Kasturi | Female | 9908853529 | kavya.kasturi23@gmail.com
24 | Kodukula Venkata Sai Ravi Teja | Venkata Sai Ravi Teja | Kodukula | Male | 7416270512 | ravitejakodukula98@gmail.com
25 | Kolla Jahnavi | Jahnavi | Kolla | Female | 8790245565 | jahnavigus0023@gmail.com
26 | Kutumbaka Varsha | Varsha | Kutumbaka | Female | 9490080818 | varshakutumbaka111@gmail.com
27 | L.Manojkumarreddy | ManojKumarReddy | L | Male | 9492079395 | lellamanojkumarreddy@gmail.com
28 | L.Rachana | Rachana | Lenkallapally | Female | 9618644046 | RLENKALLAPALLY@gmail.com
29 | M Kanchana | Kanchana | Meghavarapu | Female | 8019123143 | meghavarapuk@gmail.com
30 | M S D R Kanyaka Sabari Kumari | S D R Kanyaka Sabari Kumari | Mutta | Female | 8328144990 | sridevimutta07@gmail.com
31 | Manisha | Manisha | NA | Male | 8209264164 | manishasaps7@gmail.com
32 | Mogilicharla Sushmitha | Sushmitha | Mogilicharla | Female | 9177221255 | sushmithasiri98@gmail.com
33 | Mosarrat Perveen | Perveen | Mosarrat | Female | 7903973969 | mosarrat.786perveen@gmail.com
34 | Mounika | Mounika | Viswanadha | Female | 9652182256 | vmunni225@gmail.com
35 | Mynampati Roshanravi | Roshan | Mynampati | Male | 9491855554 | jashwitha6543@gmail.com
36 | Naga Saraswathi Vemula | NAGA SARASWATHI | VEMULA | Female | 8500036867 | saraswathinaga03@gmail.com
37 | Narasimhas Chitturi | Narasimha | Chitturi | Male | 8978116232 | narasimhachitturi1@gmail.com
38 | Nethani Abhinash Reddy | NETHANI | ABHINASH REDDY | Male | 9491109157 | abhinethani@gmail.com
39 | P.Supriya Reddy | Supriya | REDDY | Female | 8978710813 | pulususupriya@gmail.com
40 | Pallabotula Bhagya Sree | Bhagya Sree | Pallabotula | Female | 9553424242 | bhagyasri5353@gmail.com
41 | Papa Lakshmi Himaja | Lakshmi Himaja | Papa | Female | 9490167373 | papa.monica99@gmail.com
42 | Poloju Laxmi | Laxmi | Poloju | Female | 9848879665 | navyapoloju1995@gmail.com
43 | Polu Binath Yadav | POLU | BINATH YADAV | Male | 9989128381 | binathyadav5@gmail.com
44 | Prem Chand G | Prem | Chand | Male | 9705622563 | premchand.gattu@outlook.com
45 | Rachana Solthi | Rachana | Solthi | Female | 7995754235 | rachanasolthi33@gmail.com
46 | Ratnala Mounika | Mounika | Ratnala | Female | 9063868544 | monikaratnala321@gmail.com
47 | Rayala Ravi Shankar | Ravi Shankar | Rayala | Male | 7702767241 | ravishankar0798@gmail.com
48 | Sahithi Dande | Sahithi | Dande | Female | 9390746792 | maharshi4141@gmail.com
49 | Samala Suma | Suma | Samala | Female | 9704802728 | sumasamala3@gmail.com
50 | Shruti Kumari | Shruti | Kumari | Female | 8337945474 | shrutikumari03011998@gmail.com
51 | Sivarathri Naga Ravindra | Naga Ravindra | Sivarathri | Male | 9121418863 | kandruc65@gmail.com
52 | Sk Mohammud Nasib | Sk Mohammud | Nasib | Male | 7656830002 | snasib34@gmail.com
53 | V Harika | HARIKA | VITYALA | Female | 8639012849 | harikavityala97@gmail.com
54 | Vanamula Anusha | Anusha | Vanamula | Female | 9701637350 | anushavanamula98@gmail.com
55 | Vijay Shetti | VIJAY | SHETTI | Male | 9951116173 | vijayshetti699@gmail.com
56 | Voddepalli Nuthan | Voddepalli | Nuthan | Male | 8790979031 | voddepallinuthan@gmail.com
57 | Yedhurupati Amani | Yedhurupati | Amani | Female | 9182075069 | yedhurupatiamani96@gmail.com
58 | M.Aiswarya Sudha | Aiswarya | Sudha | Female | 7993380351 | raghavmaddali1357@gmail.com